# Partner Onboarding Checklist

- Partner: [Partner company name]

- Partner type: [Referral / Reseller / Agency or solution / Technology]

- Partner manager: [Your name]

- Partner contact: [Partner contact name and email]

- Approval date: [Date]

- Target date for first referral: [Approval date plus 30 days]

Copy this checklist for each new partner. Replace each owner in brackets with a name. Steps marked (Resellers) apply only to partners who sell or bill the customer, and can be deleted for referral partners.

# Before kickoff (days 0 to 5)

## Approval

☐  Review the application against your partner profile and approve or decline within [2] business days. Owner: [Partner manager]

☐  Send the approval email with one next step: book the kickoff call. Owner: [Partner manager]

☐  Create the partner record in your CRM or partner portal, with partner type and tier. Owner: [Partner manager]

☐  Assign a named partner manager and share their contact details. Owner: [Head of partnerships]

## Agreement and paperwork

☐  Send the partner agreement for e-signature. Owner: [Partner manager]

☐  Collect a Form W-9 (US partners) or Form W-8BEN or W-8BEN-E (non-US partners). Owner: [Finance]

☐  Collect payment details for commissions. Owner: [Finance]

☐  Confirm the commission rate, payment schedule and minimum payout in writing. Owner: [Partner manager]

☐  (Resellers) Confirm pricing, discount levels and how billing will work. Owner: [Partner manager]

☐  Follow up on any unsigned agreement after [3] business days. Owner: [Partner manager]

## Access

☐  Send portal access to the main partner contact. Owner: [Partner manager]

☐  Invite everyone at the partner who will refer or sell, so each referral is credited to the right person. Owner: [Partner contact]

☐  Share the partner's tracked referral link, if you use one. Owner: [Partner manager]

☐  Book the kickoff call for week 1. Owner: [Partner contact]

# Week 1

☐  Hold the kickoff call using the agenda below. Owner: [Partner manager]

☐  Agree three target clients for the first introduction. Owner: [Partner manager and partner contact]

☐  Assign the core training course. Owner: [Partner manager]

☐  Share the one-page overview, ideal customer profile and examples of good and bad referrals. Owner: [Partner manager]

☐  Share an intro email the partner can forward to a client. Owner: [Partner manager]

☐  Explain how to submit a referral and what happens after they do. Owner: [Partner manager]

☐  (Resellers) Walk through the deal registration process and protection period. Owner: [Partner manager]

☐  (Resellers) Set up a demo account. Owner: [Sales engineering]

☐  Send a kickoff recap with the agreed target clients and the date of the 30-day review. Owner: [Partner manager]

# First 30 days

☐  Core training course passed by at least one person at the partner. Owner: [Partner contact]

☐  First referral or deal registration submitted. Owner: [Partner contact]

☐  Accept or reject each referral within [2] business days, with a reason for every rejection. Owner: [Partner manager]

☐  Introduce the partner to the sales rep who will work their first referral. Owner: [Partner manager]

☐  Join the first sales call with the partner, if they want it. Owner: [Partner manager]

☐  Send a reminder if no referral has been submitted by day [21]. Owner: [Partner manager]

☐  Add the partner to the monthly partner update list. Owner: [Partner marketing]

☐  Hold the 30-day review: referrals sent, what stalled, what they need. Owner: [Partner manager]

# 60 to 90 days

☐  Update the partner on every referral as it moves through your pipeline. Owner: [Sales rep]

☐  Hold the 60-day review and agree the next two or three target clients. Owner: [Partner manager]

☐  (Resellers) Sales or technical certification completed. Owner: [Partner contact]

☐  Share a case study that matches the partner's clients. Owner: [Partner marketing]

☐  Confirm the first commission is calculated correctly and paid on schedule. Owner: [Finance]

☐  Hold the 90-day review: results against the plan, targets for next quarter. Owner: [Partner manager]

☐  Decide the partner's status: active, or paused with a check-in date. Owner: [Partner manager]

☐  Move active partners to monthly updates and quarterly reviews. Owner: [Partner manager]

☐  Record what slowed this partner down, to improve the next onboarding. Owner: [Partner manager]

# Kickoff call agenda

- Length: [45] minutes

- Attendees: [Partner manager], [Partner contact], [Other people from the partner who will refer or sell]

- Introductions (5 minutes). Who is on the call and what each person does.

- The partner's business (10 minutes). Who their clients are, what they do for them and where our product fits.

- Our ideal customer (5 minutes). Who is a good fit, who is not, with two examples of each.

- How referrals work (5 minutes). How to submit, how fast we respond and what happens next.

- How partners are paid (5 minutes). The rate, when commissions are paid and the forms we need.

- First target clients (10 minutes). Agree three clients for the first introduction and who will contact each one.

- Next steps (5 minutes). Training to complete, materials to send and the date of the 30-day review.

# Onboarding milestones

| Milestone | Target | Target date | Owner | Status |
| --- | --- | --- | --- | --- |
| Application approved | Day 0 | [Date] | [Partner manager] | [Not started] |
| Agreement signed | Day 3 | [Date] | [Partner contact] | [Not started] |
| W-9 or W-8 received | Day 3 | [Date] | [Finance] | [Not started] |
| Team invited to portal | Day 5 | [Date] | [Partner contact] | [Not started] |
| Kickoff call held | Day 7 | [Date] | [Partner manager] | [Not started] |
| Core training passed | Day 21 | [Date] | [Partner contact] | [Not started] |
| First referral submitted | Day 30 | [Date] | [Partner contact] | [Not started] |
| 30-day review held | Day 30 | [Date] | [Partner manager] | [Not started] |
| First deal closed | Day 60 to 90 | [Date] | [Sales rep] | [Not started] |
| 90-day review held | Day 90 | [Date] | [Partner manager] | [Not started] |

# Notes

[Anything that slowed this partner down, questions they asked more than once, and what to change for the next partner.]